Sri Lanka Institute of Information

Technology

PULSEOS

Web-Based Hospital Management System

LAB SHEET 02

Year 2 Semester 1

BATCH 02 | Group 60 | 2026-Y2-S1-KU-60

| Member | Student ID |
| --- | --- |
| Somarathna P.C.D.S | IT25103819 |
| Rathnayaka R.M.K.L.B | IT25103999 |
| Malwatta M.W.C.S | IT25101620 |
| Udumullage S.H.U | IT25100826 |
| Dhanasinghe K.A.K.H | IT25103992 |
| Thilakarathne H.S.K.P.N | IT25103363 |

Software Engineering | SE2030

B.Sc. (Hons) in Information Technology

# 1. Project Overview

PulseOS is a web-based Hospital Management System developed to streamline day-to-day hospital operations through a centralized digital platform. The system integrates patient registration, doctor management, appointment scheduling, pharmacy inventory management, billing and payment processing, laboratory test management, and user administration within a single environment.

The proposed system aims to reduce manual paperwork, improve hospital service delivery, enhance data accuracy, and strengthen communication among different hospital departments. Through secure role-based access, authorized users can efficiently perform healthcare and administrative tasks while maintaining patient confidentiality.

# 2. Group Members and Scrum Roles

| Member | Student ID | Scrum Role | Core Ownership / Responsibility |
| --- | --- | --- | --- |
| Somarathna P.C.D.S | IT25103819 | Product Owner | Patient Management / Backlog Acceptance |
| Rathnayaka R.M.K.L.B | IT25103999 | Scrum Master | Doctor Management / Scrum Facilitation |
| Malwatta M.W.C.S | IT25101620 | Developer | Appointment Management |
| Udumullage S.H.U | IT25100826 | Developer | Inventory & Pharmacy Management |
| Dhanasinghe K.A.K.H | IT25103992 | Developer | Billing & Payment Management |
| Thilakarathne H.S.K.P.N | IT25103363 | Developer | Laboratory & Test Management |

## Scrum Role Responsibilities

| Scrum Role | Responsibility |
| --- | --- |
| Product Owner | Owns product requirements, prioritizes backlog items, defines acceptance criteria, and accepts completed work. |
| Scrum Master | Facilitates Scrum activities, removes blockers, and ensures Scrum practices are followed correctly. |
| Developers | Design, develop, test, and integrate system functionalities while working collaboratively to achieve sprint goals. |

# 3. Core CRUD Allocation

The following CRUD allocations preserve the module ownership established during the requirements gathering phase. Each team member is responsible for managing the Create, Read, Update, and Delete (CRUD) operations of their assigned module, validating requirements, and ensuring the functionality meets the project objectives. This allocation promotes accountability, balanced workload distribution, and effective collaboration throughout the Agile development process.

| Member | Student ID | Retained CRUD Function |
| --- | --- | --- |
| Somarathna P.C.D.S | IT25103819 | Patient Management |
| Rathnayaka R.M.K.L.B | IT25103999 | Doctor Management |
| Malwatta M.W.C.S | IT25101620 | Appointment Management |
| Udumullage S.H.U | IT25100826 | Inventory & Pharmacy Management |
| Dhanasinghe K.A.K.H | IT25103992 | Billing & Payment Management |
| Thilakarathne H.S.K.P.N | IT25103363 | Laboratory & Test Management |

# 4. Identified Personas

| No. | Persona | Primary Need | Stories |
| --- | --- | --- | --- |
| 1 | Receptionist | Registers patients, schedules appointments, and manages billing activities. | 4 |
| 2 | Doctor | Diagnoses patients, prescribes medicines, and requests laboratory tests. | 4 |
| 3 | Patient | Books appointments, accesses reports, and manages personal healthcare records. | 4 |
| 4 | Pharmacist | Dispenses medicines and manages inventory records. | 4 |
| 5 | Laboratory Technician | Processes laboratory tests and manages test results. | 4 |
| 6 | System Administrator | Controls users, permissions, security, and reporting functions. | 4 |

# 5. User Stories by Persona

The following user stories are organized according to the identified personas of the PulseOS system. Each user story follows the standard Agile format, describing a specific user need and the value it provides. These stories form the basis for the Product Backlog and Sprint Planning activities carried out during the development process.

## Persona 1: Receptionist

Owner: IT25103819 — Somarathna P.C.D.S

Primary Need: Register patients, manage appointments, and support administrative hospital operations.

| ID | User Story | Priority |
| --- | --- | --- |
| PBI-01 | As a receptionist, I want to register new patients so that patient information can be stored digitally. | High |
| PBI-02 | As a receptionist, I want to update patient information so that hospital records remain accurate. | Medium |
| PBI-03 | As a receptionist, I want to schedule appointments so that patients can consult doctors efficiently. | High |
| PBI-04 | As a receptionist, I want to generate patient bills so that hospital charges can be processed correctly. | High |

## Persona 2: Doctor

Owner: IT25103999 — Rathnayaka R.M.K.L.B

Primary Need: Manage patient diagnoses, treatments, prescriptions, and laboratory requests.

| ID | User Story | Priority |
| --- | --- | --- |
| PBI-05 | As a doctor, I want to view patient medical histories so that I can make accurate diagnoses. | High |
| PBI-06 | As a doctor, I want to update treatment records so that patient information remains current. | Medium |
| PBI-07 | As a doctor, I want to create prescriptions so that patients receive appropriate medication. | High |
| PBI-08 | As a doctor, I want to request laboratory tests so that diagnoses can be made accurately. | High |

## Persona 3: Patient

Owner: IT25101620 — Malwatta M.W.C.S

Primary Need: Access healthcare services through online appointments and medical information.

| ID | User Story | Priority |
| --- | --- | --- |
| PBI-09 | As a patient, I want to register an account so that I can access hospital services online. | High |
| PBI-10 | As a patient, I want to book appointments so that I can consult doctors conveniently. | High |
| PBI-11 | As a patient, I want to view laboratory reports so that I can monitor my health information. | Medium |
| PBI-12 | As a patient, I want to view billing information so that I can track healthcare expenses. | Medium |

## Persona 4: Pharmacist

Owner: IT25100826 — Udumullage S.H.U

Primary Need: Manage medicine inventory and dispense medications accurately.

| ID | User Story | Priority |
| --- | --- | --- |
| PBI-13 | As a pharmacist, I want to view prescriptions so that medicines can be dispensed correctly. | High |
| PBI-14 | As a pharmacist, I want to update inventory records so that stock levels remain accurate. | High |
| PBI-15 | As a pharmacist, I want to monitor low-stock medicines so that replacements can be ordered on time. | Medium |
| PBI-16 | As a pharmacist, I want to record medicine dispensing transactions so that inventory records remain updated. | Medium |

## Persona 5: Laboratory Technician

Owner: IT25103363 — Thilakarathne H.S.K.P.N

Primary Need: Manage laboratory test requests, results, and laboratory reports.

| ID | User Story | Priority |
| --- | --- | --- |
| PBI-17 | As a laboratory technician, I want to receive laboratory test requests so that tests can be processed efficiently. | High |
| PBI-18 | As a laboratory technician, I want to update test statuses so that doctors can track testing progress. | Medium |
| PBI-19 | As a laboratory technician, I want to record laboratory results so that doctors can review them quickly. | High |
| PBI-20 | As a laboratory technician, I want to generate laboratory reports so that results can be shared with authorized users. | Medium |

## Persona 6: System Administrator

Owner: IT25103992 — Dhanasinghe K.A.K.H

Primary Need: Control security, users, permissions, and reporting functions.

| ID | User Story | Priority |
| --- | --- | --- |
| PBI-21 | As a system administrator, I want to create user accounts so that authorized users can access the system. | High |
| PBI-22 | As a system administrator, I want to assign roles and permissions so that user access can be controlled securely. | High |
| PBI-23 | As a system administrator, I want to monitor audit logs so that system activities can be tracked. | Medium |
| PBI-24 | As a system administrator, I want to generate operational reports so that hospital performance can be monitored. | Low |

# 6. Product Backlog

The product backlog is prioritized according to business value, dependency order, and system importance. High-priority items represent critical hospital operations and security requirements. Medium-priority items support operational workflows, while low-priority items focus on additional administrative enhancements.

## Priority Rationale and Distribution

| Priority | Count | Description |
| --- | --- | --- |
| High | 13 | Core hospital functions and security-related features |
| Medium | 10 | Supporting hospital operations and management features |
| Low | 1 | Reporting enhancement and administrative support |

## Prioritized Product Backlog (All 24 Items)

| Rank | ID | Persona | User Story | Priority |
| --- | --- | --- | --- | --- |
| 1 | PBI-21 | System Administrator | As a system administrator, I want to create user accounts so that authorized users can access the system. | High |
| 2 | PBI-22 | System Administrator | As a system administrator, I want to assign roles and permissions so that user access can be controlled securely. | High |
| 3 | PBI-09 | Patient | As a patient, I want to register an account so that I can access hospital services online. | High |
| 4 | PBI-01 | Receptionist | As a receptionist, I want to register new patients so that patient information can be stored digitally. | High |
| 5 | PBI-03 | Receptionist | As a receptionist, I want to schedule appointments so that patients can consult doctors efficiently. | High |
| 6 | PBI-10 | Patient | As a patient, I want to book appointments so that I can consult doctors conveniently. | High |
| 7 | PBI-05 | Doctor | As a doctor, I want to view patient medical histories so that I can make accurate diagnoses. | High |
| 8 | PBI-08 | Doctor | As a doctor, I want to request laboratory tests so that diagnoses can be made accurately. | High |
| 9 | PBI-13 | Pharmacist | As a pharmacist, I want to view prescriptions so that medicines can be dispensed correctly. | High |
| 10 | PBI-17 | Laboratory Technician | As a laboratory technician, I want to receive laboratory test requests so that tests can be processed efficiently. | High |
| 11 | PBI-07 | Doctor | As a doctor, I want to create prescriptions so that patients receive appropriate medication. | High |
| 12 | PBI-19 | Laboratory Technician | As a laboratory technician, I want to record laboratory results so that doctors can review them quickly. | High |
| 13 | PBI-14 | Pharmacist | As a pharmacist, I want to update inventory records so that stock levels remain accurate. | High |
| 14 | PBI-04 | Receptionist | As a receptionist, I want to generate patient bills so that hospital charges can be processed correctly. | High |
| 15 | PBI-11 | Patient | As a patient, I want to view laboratory reports so that I can monitor my health information. | Medium |
| 16 | PBI-20 | Laboratory Technician | As a laboratory technician, I want to generate laboratory reports so that results can be shared with authorized users. | Medium |
| 17 | PBI-15 | Pharmacist | As a pharmacist, I want to monitor low-stock medicines so that replacements can be ordered on time. | Medium |
| 18 | PBI-16 | Pharmacist | As a pharmacist, I want to record medicine dispensing transactions so that inventory records remain updated. | Medium |
| 19 | PBI-18 | Laboratory Technician | As a laboratory technician, I want to update test statuses so that doctors can track testing progress. | Medium |
| 20 | PBI-06 | Doctor | As a doctor, I want to update treatment records so that patient information remains current. | Medium |
| 21 | PBI-12 | Patient | As a patient, I want to view billing information so that I can track healthcare expenses. | Medium |
| 22 | PBI-23 | System Administrator | As a system administrator, I want to monitor audit logs so that system activities can be tracked. | Medium |
| 23 | PBI-24 | System Administrator | As a system administrator, I want to generate operational reports so that hospital performance can be monitored. | Low |
| 24 | PBI-02 | Receptionist | As a receptionist, I want to update patient information so that hospital records remain accurate. | Medium |

# 7. Sprint Planning Approach

The 24 Product Backlog items have been divided into four sprints based on business value, feature dependencies, and system priorities. Foundational functionalities such as user account management, role-based access control, patient registration, and appointment booking are scheduled in the first sprint because other hospital operations depend on them. Core medical functionalities including patient records, prescriptions, laboratory requests, and pharmacy services are implemented in the following sprints. Billing, reporting, audit logging, and system integration activities are planned for later sprints after the core healthcare services have been completed and tested.

| Sprint | Priority Focus | Goal | Stories |
| --- | --- | --- | --- |
| Sprint 1 | System Foundation | Establish the foundation of PulseOS by implementing user management, role-based access control, patient registration, and appointment booking functionalities required for the system's core operations. | PBI-21, PBI-22, PBI-09, PBI-01, PBI-03, PBI-10 |
| Sprint 2 | Core Medical Operations | Develop the core healthcare services of PulseOS by enabling patient medical record access, prescription management, laboratory test requests, and laboratory result processing functionalities. | PBI-05, PBI-08, PBI-13, PBI-17, PBI-07, PBI-19 |
| Sprint 3 | Pharmacy, Laboratory & Billing | Implement essential operational services by developing inventory management, pharmacy functions, billing processes, laboratory report generation, and patient access to healthcare information. | PBI-14, PBI-04, PBI-11, PBI-20, PBI-15, PBI-16 |
| Sprint 4 | Administration & Finalization | Complete the PulseOS system by implementing administrative controls, audit logging, reporting features, patient record maintenance, and final system integration and testing activities. | PBI-18, PBI-06, PBI-12, PBI-23, PBI-24, PBI-02 |

7.1 Sprint 1

Sprint Goal — Establish the foundation of PulseOS by implementing user management, role-based access control, patient registration, and appointment booking functionalities required for the system's core operations.

### Selected User Stories (Based on Priority and Dependencies)

| Sprint ID | PBI | User Story | Priority |
| --- | --- | --- | --- |
| SP1-01 | PBI-21 | As a system administrator, I want to create user accounts so that authorized users can access the system. | High |
| SP1-02 | PBI-22 | As a system administrator, I want to assign roles and permissions so that user access can be controlled securely. | High |
| SP1-03 | PBI-09 | As a patient, I want to register an account so that I can access hospital services online. | High |
| SP1-04 | PBI-01 | As a receptionist, I want to register new patients so that patient information can be stored digitally. | High |
| SP1-05 | PBI-03 | As a receptionist, I want to schedule appointments so that patients can consult doctors efficiently. | High |
| SP1-06 | PBI-10 | As a patient, I want to book appointments so that I can consult doctors conveniently. | High |

### Sprint Backlog — Task Assignments and Ownership (Total: 70 Hours)

| Task ID | Linked PBI | Task | Owner | Est. Hours |
| --- | --- | --- | --- | --- |
| T-01.1 | All Sprint 1 PBIs | Facilitate backlog refinement and finalize acceptance criteria for Sprint 1 stories | Somarathna P.C.D.S (PO) | 4 |
| T-01.2 | PBI-01 | Analyze patient registration requirements and data validation rules | Somarathna P.C.D.S | 3 |
| T-01.3 | PBI-01 | Implement patient registration CRUD functionality | Somarathna P.C.D.S | 5 |
| T-01.4 | All Sprint 1 PBIs | Facilitate sprint planning, daily stand-ups and sprint review | Rathnayaka R.M.K.L.B (SM) | 4 |
| T-01.5 | PBI-03 / PBI-10 | Define appointment scheduling workflow and doctor-availability rules | Rathnayaka R.M.K.L.B | 3 |
| T-01.6 | PBI-21 | Design authentication and secure login workflow specification | Rathnayaka R.M.K.L.B | 5 |
| T-01.7 | PBI-09 | Design and implement patient account registration interface | Malwatta M.W.C.S | 5 |
| T-01.8 | PBI-03 | Implement appointment scheduling functionality | Malwatta M.W.C.S | 4 |
| T-01.9 | PBI-10 | Implement appointment booking and confirmation workflow | Malwatta M.W.C.S | 3 |
| T-01.10 | PBI-21 | Implement user account creation module | Udumullage S.H.U | 6 |
| T-01.11 | PBI-21 / PBI-09 | Unit-test account creation and patient registration flows | Udumullage S.H.U | 5 |
| T-01.12 | PBI-22 | Implement role-based access control and permission assignment | Dhanasinghe K.A.K.H | 6 |
| T-01.13 | PBI-22 | Test RBAC rules across all defined user roles | Dhanasinghe K.A.K.H | 5 |
| T-01.14 | All Sprint 1 PBIs | Design database schema for Users, Patients and Appointments | Thilakarathne H.S.K.P.N | 6 |
| T-01.15 | All Sprint 1 PBIs | Set up development/testing environment and Sprint 1 integration test plan | Thilakarathne H.S.K.P.N | 6 |

7.2 Sprint 2

Sprint Goal — Develop the core healthcare services of PulseOS by enabling patient medical record access, prescription management, laboratory test requests, and laboratory result processing functionalities.

### Selected User Stories (Based on Priority and Dependencies)

| Sprint ID | PBI | User Story | Priority |
| --- | --- | --- | --- |
| SP2-01 | PBI-05 | As a doctor, I want to view patient medical histories so that I can make accurate diagnoses. | High |
| SP2-02 | PBI-08 | As a doctor, I want to request laboratory tests so that diagnoses can be made accurately. | High |
| SP2-03 | PBI-13 | As a pharmacist, I want to view prescriptions so that medicines can be dispensed correctly. | High |
| SP2-04 | PBI-17 | As a laboratory technician, I want to receive laboratory test requests so that tests can be processed efficiently. | High |
| SP2-05 | PBI-07 | As a doctor, I want to create prescriptions so that patients receive appropriate medication. | High |
| SP2-06 | PBI-19 | As a laboratory technician, I want to record laboratory results so that doctors can review them quickly. | High |

### Sprint Backlog — Task Assignments and Ownership (Total: 70 Hours)

| Task ID | Linked PBI | Task | Owner | Est. Hours |
| --- | --- | --- | --- | --- |
| T-02.1 | All Sprint 2 PBIs | Refine Sprint 2 backlog and define acceptance criteria for the medical workflow stories | Somarathna P.C.D.S (PO) | 4 |
| T-02.2 | PBI-05 | Validate clinical data-access rules and patient-privacy requirements for the medical history module | Somarathna P.C.D.S | 7 |
| T-02.3 | All Sprint 2 PBIs | Facilitate Sprint 2 Scrum events and resolve blockers | Rathnayaka R.M.K.L.B (SM) | 3 |
| T-02.4 | PBI-05 | Implement patient medical-history viewing functionality | Rathnayaka R.M.K.L.B | 4 |
| T-02.5 | PBI-07 | Implement prescription creation and management functionality | Rathnayaka R.M.K.L.B | 5 |
| T-02.6 | PBI-05 / PBI-07 | Integrate appointment records with the consultation and medical-history workflow | Malwatta M.W.C.S | 5 |
| T-02.7 | All Sprint 2 PBIs | Regression-test the appointment module against Sprint 2 changes | Malwatta M.W.C.S | 6 |
| T-02.8 | PBI-13 | Design prescription-viewing workflow for pharmacists | Udumullage S.H.U | 5 |
| T-02.9 | PBI-13 | Implement prescription viewing and integration with the doctor module | Udumullage S.H.U | 7 |
| T-02.10 | PBI-04 (prep) | Prepare billing schema to accommodate future consultation and laboratory charges | Dhanasinghe K.A.K.H | 6 |
| T-02.11 | All Sprint 2 PBIs | Support integration testing between the doctor, pharmacy and laboratory modules | Dhanasinghe K.A.K.H | 6 |
| T-02.12 | PBI-08 / PBI-17 | Implement the laboratory test request module | Thilakarathne H.S.K.P.N | 7 |
| T-02.13 | PBI-19 | Implement laboratory result entry and validation | Thilakarathne H.S.K.P.N | 5 |

7.3 Sprint 3

Sprint Goal — Implement essential operational services by developing inventory management, pharmacy functions, billing processes, laboratory report generation, and patient access to healthcare information.

### Selected User Stories (Based on Priority and Dependencies)

| Sprint ID | PBI | User Story | Priority |
| --- | --- | --- | --- |
| SP3-01 | PBI-14 | As a pharmacist, I want to update inventory records so that stock levels remain accurate. | High |
| SP3-02 | PBI-04 | As a receptionist, I want to generate patient bills so that hospital charges can be processed correctly. | High |
| SP3-03 | PBI-11 | As a patient, I want to view laboratory reports so that I can monitor my health information. | Medium |
| SP3-04 | PBI-20 | As a laboratory technician, I want to generate laboratory reports so that results can be shared with authorized users. | Medium |
| SP3-05 | PBI-15 | As a pharmacist, I want to monitor low-stock medicines so that replacements can be ordered on time. | Medium |
| SP3-06 | PBI-16 | As a pharmacist, I want to record medicine dispensing transactions so that inventory records remain updated. | Medium |

### Sprint Backlog — Task Assignments and Ownership (Total: 70 Hours)

| Task ID | Linked PBI | Task | Owner | Est. Hours |
| --- | --- | --- | --- | --- |
| T-03.1 | All Sprint 3 PBIs | Refine Sprint 3 backlog and approve billing/inventory acceptance criteria | Somarathna P.C.D.S (PO) | 4 |
| T-03.2 | PBI-11 | Implement patient laboratory-report viewing functionality | Somarathna P.C.D.S | 8 |
| T-03.3 | All Sprint 3 PBIs | Facilitate Sprint 3 Scrum events and manage risks | Rathnayaka R.M.K.L.B (SM) | 3 |
| T-03.4 | All Sprint 3 PBIs | Support integration testing between the billing, pharmacy and laboratory modules | Rathnayaka R.M.K.L.B | 8 |
| T-03.5 | PBI-04 | Link appointment records to billing for consultation-charge integration | Malwatta M.W.C.S | 6 |
| T-03.6 | All Sprint 1-3 PBIs | Conduct system-wide regression testing across completed modules | Malwatta M.W.C.S | 6 |
| T-03.7 | PBI-14 | Implement inventory record management functionality | Udumullage S.H.U | 5 |
| T-03.8 | PBI-15 | Implement low-stock monitoring and alerting functionality | Udumullage S.H.U | 4 |
| T-03.9 | PBI-16 | Implement medicine-dispensing transaction module | Udumullage S.H.U | 3 |
| T-03.10 | PBI-04 | Define billing calculation rules and charge categories | Dhanasinghe K.A.K.H | 4 |
| T-03.11 | PBI-04 | Implement patient billing generation functionality | Dhanasinghe K.A.K.H | 4 |
| T-03.12 | PBI-04 | Integrate appointment, laboratory and pharmacy charges into billing records | Dhanasinghe K.A.K.H | 4 |
| T-03.13 | PBI-20 | Develop laboratory report generation and formatting module | Thilakarathne H.S.K.P.N | 6 |
| T-03.14 | PBI-11 / PBI-20 | Test laboratory reporting against the patient-view integration | Thilakarathne H.S.K.P.N | 5 |

7.4 Sprint 4

Sprint Goal — Complete the PulseOS system by implementing administrative controls, audit logging, reporting features, patient record maintenance, and final system integration and testing activities.

### Selected User Stories (Based on Priority and Dependencies)

| Sprint ID | PBI | User Story | Priority |
| --- | --- | --- | --- |
| SP4-01 | PBI-18 | As a laboratory technician, I want to update test statuses so that doctors can track testing progress. | Medium |
| SP4-02 | PBI-06 | As a doctor, I want to update treatment records so that patient information remains current. | Medium |
| SP4-03 | PBI-12 | As a patient, I want to view billing information so that I can track healthcare expenses. | Medium |
| SP4-04 | PBI-23 | As a system administrator, I want to monitor audit logs so that system activities can be tracked. | Medium |
| SP4-05 | PBI-24 | As a system administrator, I want to generate operational reports so that hospital performance can be monitored. | Low |
| SP4-06 | PBI-02 | As a receptionist, I want to update patient information so that hospital records remain accurate. | Medium |

### Sprint Backlog — Task Assignments and Ownership (Total: 70 Hours)

| Task ID | Linked PBI | Task | Owner | Est. Hours |
| --- | --- | --- | --- | --- |
| T-04.1 | All Sprint 4 PBIs | Review completed backlog items and approve release deliverables | Somarathna P.C.D.S (PO) | 4 |
| T-04.2 | PBI-02 | Implement patient-information update functionality | Somarathna P.C.D.S | 8 |
| T-04.3 | All Sprint 4 PBIs | Facilitate sprint review, retrospective and release-readiness activities | Rathnayaka R.M.K.L.B (SM) | 4 |
| T-04.4 | PBI-06 | Implement treatment-record update functionality | Rathnayaka R.M.K.L.B | 8 |
| T-04.5 | All modules | Coordinate final system integration testing across all six modules | Malwatta M.W.C.S | 5 |
| T-04.6 | All modules | Conduct user-acceptance testing and log defects for resolution | Malwatta M.W.C.S | 6 |
| T-04.7 | All modules | Support final integration testing for the pharmacy and inventory workflows | Udumullage S.H.U | 5 |
| T-04.8 | All modules | Perform release verification and documentation review | Udumullage S.H.U | 6 |
| T-04.9 | PBI-12 | Implement patient billing-information view | Dhanasinghe K.A.K.H | 4 |
| T-04.10 | PBI-23 | Design and implement audit-logging functionality | Dhanasinghe K.A.K.H | 4 |
| T-04.11 | PBI-24 | Develop the operational reporting module | Dhanasinghe K.A.K.H | 4 |
| T-04.12 | PBI-18 | Implement laboratory test-status tracking functionality | Thilakarathne H.S.K.P.N | 7 |
| T-04.13 | PBI-18 | Final testing of the laboratory module ahead of release | Thilakarathne H.S.K.P.N | 5 |

8. Ownership Summary

## 8.1 Sprint Ownership Summary

| Sprint | Primary Module Focus | Total Hours |
| --- | --- | --- |
| Sprint 1 | Patient Management, Appointment Management, User & Access Administration | 70 |
| Sprint 2 | Doctor Management, Laboratory Management, Pharmacy Management | 70 |
| Sprint 3 | Pharmacy Management, Billing Management, Laboratory Management | 70 |
| Sprint 4 | Audit Logging, Reporting, Patient Record Maintenance, System Integration | 70 |
| Total Project Effort | All Modules | 280 |

## 8.2 Member Ownership Summary

Ownership hours below reflect direct task ownership across all four sprints, recalculated to correct the imbalance in the original report. The remaining project effort consists of collaborative activities such as sprint planning, sprint reviews, integration testing, bug fixing and shared validation, which are distributed across the team within each sprint's task list above.

| Member (Student ID) | Scrum Role | Owned Module | Major Responsibility | Owned Task IDs | Total Est Hrs |
| --- | --- | --- | --- | --- | --- |
| Somarathna P.C.D.S (IT25103819) | Product Owner | Patient Management | Owns the backlog and acceptance criteria; delivers Patient Management (registration, updates, report views) across all sprints. | T-01.1, T-01.2, T-01.3, T-02.1, T-02.2, T-03.1, T-03.2, T-04.1, T-04.2 | 47 |
| Rathnayaka R.M.K.L.B (IT25103999) | Scrum Master | Doctor Management | Facilitates Scrum events and blocker resolution; delivers Doctor Management (history, prescriptions, treatment updates), mainly Sprints 2 & 4. | T-01.4, T-01.5, T-01.6, T-02.3, T-02.4, T-02.5, T-03.3, T-03.4, T-04.3, T-04.4 | 47 |
| Malwatta M.W.C.S (IT25101620) | Developer | Appointment Management | Delivers Appointment Management in Sprint 1; leads cross-module integration, regression and final UAT in Sprints 2-4. | T-01.7, T-01.8, T-01.9, T-02.6, T-02.7, T-03.5, T-03.6, T-04.5, T-04.6 | 46 |
| Udumullage S.H.U (IT25100826) | Developer | Inventory & Pharmacy Management | Builds account-management infrastructure (Sprint 1) and prescription viewing (Sprint 2); owns Inventory & Pharmacy (Sprint 3); supports release verification (Sprint 4). | T-01.10, T-01.11, T-02.8, T-02.9, T-03.7, T-03.8, T-03.9, T-04.7, T-04.8 | 46 |
| Dhanasinghe K.A.K.H (IT25103992) | Developer | Billing & Payment Management | Implements RBAC (Sprint 1) and billing-schema prep (Sprint 2); delivers Billing & Payment (Sprint 3); leads admin features - billing view, audit logs, reporting (Sprint 4). | T-01.12, T-01.13, T-02.10, T-02.11, T-03.10, T-03.11, T-03.12, T-04.9, T-04.10, T-04.11 | 47 |
| Thilakarathne H.S.K.P.N (IT25103363) | Developer | Laboratory & Test Management | Sets up DB schema & test environment (Sprint 1); owns Laboratory & Test Management end-to-end across Sprints 2-4. | T-01.14, T-01.15, T-02.12, T-02.13, T-03.13, T-03.14, T-04.12, T-04.13 | 47 |